## Sheet1
Pollution Detection and Prediction System Gannt Chart
June-July | August-September | October-November | December-January | February-March
Understanding problem statement
Project ideation
Identifying and selecting optimum features
Literature survey
Process flow designing
Dummy data generation
Studying ML algorithms
Implementation of ML algorithms
Studying of air dispersion models
Adding changes to the process flow design to incorporate low cost sensors
Studying of Inverse air dispersion models
Designing of IOT Module and Implementation
Deploying the IOT module to collect real world data
Building Cloud server API to store data collected by the IOT module
Implementation of air dispersion models
Implementation of inverse air dispersion models